# Futuril — Development Phases (Revised for Solo Build)

Revision notes: reorganized from 13 feature-themed phases into a sequenced build plan with an explicit MVP cut line, effort estimates, and a stated wedge feature. Original feature scope is preserved in full below the MVP line — nothing was deleted, only resequenced.

# Why this revision

The original 13 phases are correct in scope but organized by feature theme rather than by build order. For a solo, first-time builder this creates two risks: (1) no signal for what must exist before anything is validated by real users, and (2) expensive, low-validation work (3D landing experience, voice AI, multilingual) sits early enough to consume months before the core loop even works. This revision keeps every original feature — none are cut — but sequences them so a working, testable product exists in roughly five months of part-time solo work, with everything after the MVP line added once real usage data justifies the investment.

# Timeline Overview

| Stage | Focus | Est. weeks (solo, part-time) | Ships to users? |
| --- | --- | --- | --- |
| A | Foundation (auth, DB, shell, deploy) | 1-3 | No |
| B | Onboarding + Career DNA | 4-6 | Internal test |
| C | Career Compass | 7-8 | Internal test |
| D | Skill Graph v1 (relational, not full graph DB) | 9-10 | No |
| E | AI Pathway (fixed-length roadmaps, one career at a time) | 11-13 | Internal test |
| F | Learning Hub core (the wedge feature) | 14-18 | YES - closed beta |
| G | Dashboard | 19-20 | YES - closed beta |
| — MVP LINE — | Ship, get real students using it, gather retention data | ~5 months total | MVP LAUNCH |
| H | Practice Engine | post-MVP | Public |
| I | Project Lab + AI mentor | post-MVP | Public |
| J | Portfolio & Resume Studio | post-MVP | Public |
| K | Career Readiness Score + Opportunity Engine | post-MVP | Public |
| L | Kiki full companion (memory, voice, adaptive roadmap) | post-MVP | Public |
| M | Multilingual + India-first expansion | post-MVP | Public |
| N | 3D experience & visual polish layer | post-MVP | Public |
| O | Premium monetization layer | post-MVP | Public |

# MVP Scope Detail (Stages A–G)

## Stage A — Foundation

- Auth: email/password + Google OAuth (via Supabase Auth)

- App shell, navigation, minimal flat design system — no 3D yet

- Core DB schema: users, skills, careers, pathway_levels, learning_sessions

- CI/CD: GitHub → Vercel auto-deploy

## Stage B — Onboarding + Career DNA

- 5-step onboarding exactly as specified in the PRD (education stage, skill level, goals, time availability)

- Career DNA generated by a single structured LLM call → interest profile, strengths, learning style, archetype

- Simple bar-chart / text visualization first; the animated DNA visual is a Stage N polish item

## Stage C — Career Compass

- Curated database of 15-20 careers to start (not an open-ended career universe yet)

- Match-percentage cards + "Why this recommendation" explanation (cheap, high differentiation — keep this early)

## Stage D — Skill Graph v1

- Relational model (skills, prerequisites, user_skill_scores) in Postgres — not a dedicated graph database yet

- Powers skill-gap analysis for Compass and Pathway

## Stage E — AI Pathway

- Fixed-length roadmap per career (e.g. 20-30 levels), one active career per user at a time

- Weekly goals / daily tasks derived from stated time availability

- Adaptive re-planning is deferred to Stage L — ship a static-but-personalized roadmap first

## Stage F — Learning Hub core (the wedge feature)

- Accept PDF / pasted text / links

- "Teach me this" → pick 3-4 modes to start (Explain, Quiz, Flashcards, Summary); add Deep Dive, Feynman, Story modes post-MVP

- This feature alone is demoable and shareable — treat it as the thing you show people to get first users, feedback, and conviction

## Stage G — Dashboard

- Today's mission, pathway progress, skill progress bars, streak

- Skip the 3D compass and career-galaxy visuals here — flat cards are enough to validate the loop

# Post-MVP Phases (Stages H–O)

Everything below preserves the full original scope from the Development Phases and PRD documents. Sequence and pacing should be set after MVP retention data is in hand — build the thing users actually ask for next, not necessarily this exact order.

## Stage H — Practice Engine

- Daily/weekly challenges, skill exercises, scenario-based practice, active recall

## Stage I — Project Lab + AI Mentor

- Safe / Growth / Challenge project generation

- AI mentor across idea → requirements → planning → implementation → debugging → deployment

- "You copied this but may not understand it" comprehension check

## Stage J — Portfolio & Career Studio

- Career portfolio, project showcase

- Resume builder, job-description matching ("72% match"), ATS optimization

- Mock interviews

## Stage K — Career Readiness & Opportunities

- Offer-Ready Score across skill/project/portfolio/resume/interview readiness

- Opportunity Engine: internships, jobs, hackathons, scholarships

## Stage L — Kiki, full companion

- Start Kiki earlier and cheaply as a context-aware text chat during Stage F (system prompt fed by Career DNA + progress) — this de-risks the hardest feature by testing it early without the cost of voice/memory infra

- Formalize modes (Tutor, Career Coach, Project Mentor, Interviewer, Motivation, Focus) here

- Add long-term memory, weekly check-ins, adaptive roadmap triggers, and Voice Mode last — these are the most expensive and hardest-to-validate pieces

## Stage M — Multilingual & India-First

- Tamil / Hindi / English support, Indian degree-to-career mapping, local salary and opportunity data

## Stage N — 3D Experience & Visual Polish

- Career Galaxy landing page, animated Career DNA, 3D pathway/dashboard elements

- Deliberately last: 3D is emotional/branding value, not core-loop value, and is easy to lose weeks to as a solo builder before the product is proven

## Stage O — Premium Layer

- Advanced Kiki, advanced interview simulation, premium analytics, personalized mentorship, advanced opportunity matching

- Pair with a payments integration (see Tech Stack document) once there is a free-tier user base to convert